## Slide 1: Managing and Tracking the Software Project
Not every group is a team, and not every team is effective. Glenn Parker
If you want to be incrementally better: Be competitive. If you want to be exponentially better: Be cooperative

## Slide 2: Questions from a Customer
Do you understand my problem and needs?
Can you design a system to solve my problems or satisfy my needs?
How long will it take to develop the system?
How much will it cost to develop the system?

## Slide 3: Project Planning
Before starting
  Establish system’s scope and objectives
  Consider alternative solutions
  Identify technical and management constraints
As a Project Manager
  Decompose the product function (FD)
  Select an appropriate process model
  Select the task set for the project
  Decompose the tasks into smaller work items (WBS)
  Estimate effort for each task/work item
  Estimate completion time of the project (Task/Activity Network)

## Slide 4: Project Schedule (Contd.)
Understanding customer’s needs by listing all project deliverables
  Documents
  Demonstrations of function
  Demonstrations of subsystems
  Demonstrations of accuracy
  Demonstrations of reliability, performance or security
Determining milestones and activities to produce the deliverables

## Slide 5: Project Schedule (Contd.)
Activity: takes place over a period of time
Milestone: completion of an activity -- a particular point in time
Precursor: event or set of events that must occur in order for an activity to start
Duration: length of time needed to complete an activity
Due date: date by which an activity must be completed

## Slide 6: Project Schedule (Contd.)
Project development can be separated into a succession of phases which are composed of steps, which are composed of activities (Work Breakdown Structure)

## Slide 7: Work Break Down Structure(Contd.)
Work breakdown structure depicts the project as a set of discrete pieces of work

## Slide 8: Activity Networks
Activity networks depict the dependencies among activities
Activity networks can be of two types
  AoA: Activity on Arc
  AoN: Activity on Node

## Slide 9: Project Types
Concept Development
  To explore new business concept
New Application Development
  As a consequence of specific customer request
Application Enhancement
  Modifications to existing functions, performance, interfaces of software; observable by the end user
Application Maintenance
  Correct, adapt, extend existing software; not immediately obvious to end user
Reengineering Projects
  Redevelop an existing system

## Slide 10: Concept Development Projects
Usually initiated to explore some new business concept or application of some new technology
Task set might be like:
  Scope the concept
  Develop preliminary plan of the concept: develop the ability to undertake the work
  Assess the technology risk
  Develop proof of concept
  Implement the concept
  Get customer feedback

## Slide 11: WBS for CDP

## Slide 12: WBS for CDP (Contd.)

## Slide 13: Activity on Arrow(AOA)

## Slide 14: Activity on Node(AON)

## Slide 15: Estimating Completion Critical Path Method
Minimum amount of time required to complete a project
  Reveals those activities that are most critical to completing the project on time
Real time (actual time): estimated amount of time required for the activity to be completed

## Slide 16: Estimating Completion Critical Path Method
Earliest Finish =Earliest Start+duration
Latest Start=Latest Finish-Duration
Slack time = Delayed time
  Formulae=Latest Finish-Earliest Finish
Critical path: the slack at every activity is zero
  can be more than one in a project schedule

## Slide 17: Program Evaluation Review Technique (PERT) Chart/ Critical Path Method

## Slide 18: Critical Path Method

## Slide 19: Critical Path Method

## Slide 20: Gantt Chart

## Slide 21: Gantt Chart

## Slide 22: References
Pfleeger SE Book
Pressman SE Book
Acknowledgement
A few slides have been reused from UCF slides for the SE course